## Sprint 1
# | Type | Module | Section | Description | Target Hrs. | Assignee | Actual Hrs. | Status
1 | Model | General |  | Initialize Database - create localhost database (based on Final ERD wiith indexing) | 12 | Christian | 16 | done
2 | Model | General |  | Populate Database with Dummy Data - populate encounters and patient | 8 | Christian | 8 | done
3 | View | User Management | Registration | Personnel number - doctor can input his personnel_number | 5 | Louie | 5 | done
4 | Model | User Management | Registration | Validate Personnel Number - validate personnel number if it exists in SegHIS |  | Ipong |  | backlogged
5 | Model | User Management | Registration | Get Username and Password - retrieve username and password from SegHIS based on personnel number |  | Jessie |  | backlogged
6 | View | User Management | Registration | Enter Credentials from SegHIS - doctor can input his username and password from SegHIS | 5 | Joy | 5 | done
7 | Controller | User Management | Registration | Credentials verification - compare doctor SegHIS credentials with inputted credentials | 2 | Jake | 2 | done
8 | Model | User Management | Registration | Retrieve SegHIS credentials - retrieve username and password of SegHIS account from SegHIS |  | Chanly |  | backlogged
9 | Model | General |  | Initial Sync with SegHIS - get all data from SegHIS database based on doctor info and save to localhost(encounters) | 15 | Chanly |  | backlogged
10 | Model | General |  | Initial Sync with SegHIS - get all data from SegHIS database based on doctor info and save to localhost(departments) | 15 | Justine |  | backlogged
11 | View | User Management | Registration | Create Account - doctor can fill up sign up form(username, password, confirm) | 5 | Philipp | 5 | done
12 | Model | User Management | Registration | Create Account - save successful registration credentials to database | 5 | Jessie | 5 | done
13 | View | User Management | Login | Login Page - login page ("invalid login" dialog box included) | 2 | Ipong | 2 | done
14 | Controller | User Management | Login | Validate credentials - from database values | 5 | Ipong | 5 | done
15 | View | General | Navigation Bar | Implement Action Bar - implement navigation drawer | 5 | Ipong | 5 | done
16 | View | General | Navigation Bar | Implement Action Bar - add functionality to navigation items | 5 | Justine | 5 | done
17 | View | General | Navigation Bar | Implement Action Bar -add home button | 5 | Ipong | 5 | done
18 | View | General | Home Page | Icons - make icons for home page | 10 | Philipp | 10 | done
19 | View | General | Home Page | Icons - add functionality to icon buttons | 5 | Justine | 5 | done
20 | View | General | Home Page | Icons - add functionality to icon buttons | 5 | Ipong | 5 | done
21 | Controller | General | Logout | Logout - allow doctor to logout (navigation drawer) | 2 | Alvin | 2 | done
22 | View | Patient (Offline/Online) | Patient List | Patient List Layout - make layout for patient module first page | 8 | Philipp | 8 | done
23 | Controller | Patient(Offline/Online) | Patient List | Auto Suggest Search Bar - google like search | 5 | Ipong |  | backlogged
24 | Model | Patient (Offline) | Patient List | Search Patient Name - retrieve all names/pid of patient that match search string from localhost | 8 | Jessie | 8 | done
25 | Model | Patient (Online) | Patient List | Search Patient Name - retrieve all names/pid of patient that match search string from SegHIS (with respect to department) |  | Justine/Chanly |  | backlogged
26 | Controller | Patient(Offline/Online) | Patient List | Handle Select Patient - link the patent list page to encounter list page |  | Alvin |  | backlogged
27 | View | Patient (Offline/Online) | Encounter List | Encounters List Page Layout - make layout for listing all encounters for active patient | 5 | Philipp | 5 | done
28 | Model | Patient (Offline/Online) | Encounter List | Retrieve Encounters - retrieve all encounters of active patient from localhost | 5 | Christian | 4 | done
29 | Model | Patient (Offline/Online) | Encounter List | Retrieve Encounters - retrieve all encounters of active patient from SegHIS |  | Chanly |  | backlogged
30 | Controller | Patient (Offline/Online) | Encounter List | Handle Select Encounter - link encouter list page to patient info |  | Alvin |  | backlogged
31 | View | Patient (Offline/Online) | Patient Info | Encounter-Patient Info Layout - make layout for encounter-patient info page (with "Tag as my patient" button)) | 5 | Philipp | 5 | done
32 | Model | Patient (Offline/Online) | Patient Info | Get Patient Info - get necessary patient data in patient info page based on active patient (pid) from localhost | 8 | Jake |  | backlogged
33 | Controller | Patient (Offline/Online) | Patient Info | Integrate Patient Data - display necessary patient data for a specific encounter in encounter-patient info page | 8 | Jessie |  | backlogged
34 | Controller | Patient(Online) | Patient Tagging | Handle Tag Patient - handle click of "tag as my patient" button |  | Alvin |  | backlogged
35 | Model | Patient(Online) | Patient Tagging | Handle Tag Patient - update localhost, get encounter data from SegHIS to localhost | 8 | Alvin |  | backlogged
36 | Model | Patient(Online) | Patient Tagging | Handle Tag Patient - update SegHIS database (POST method) |  | Alvin |  | backlogged
37 | View | Patient (Offline/Online) | Referral | Referral History - make layout for referral history | 5 | Philipp | 5 | done
38 | View | Patient(Online) | Referral | Referral Request - make layout for making a referral request | 5 | Philipp | 5 | done
39 | Model | Patient(Offline/Online) | Referral | Retrieve Referrals - retrieve all referrals of active patient from localhost |  | Jake |  | backlogged
40 | Controller | Patient(Offline/Online) | Referral | Setup New Request - setup options for making a new referral |  | Alvin |  | backlogged
42 | Model | Patient(Offline/Online) | Referral | Save New Referral - handle saving of referral to localhost | 6 | Christian |  | backlogged
43 | Controller | Patient (Offline/Online) | Patient List | Handle Icon Click - handle click of Patient Icon | 1 | Jake | 1 | done
|  |  |  | TOTAL | 146 |  | 131 | 89.73% | <-- invalid
|  |  |  | GOALS: | STATUS
|  |  |  | To implement the structure of the database and have it ready for use | done
|  |  |  | To setup the layout of the Home Page of the application | done
|  |  |  | To partially implement the proposed "Patient" module upto "tag as my patient" functionality | failed

## Sprint 2
# | Type | Module | Section | Description | Target Hrs. | Assignee | Actual Hrs. | Status | Task Type
1 | Controller | User Management | Registration | Setup Registration Activity | 8 | Alvin | 9 | done
2 | Model | User Management | Login | Setup Login Activity | 1 | Alvin | 1 | done | Unplanned
3 | Controller | User Management | Initialization | Save Client ID to database | 2 | Alvin | 2 | done | Unplanned
4 | Controller | User Management | API | Retrieve Tokens | 9 | Alvin | 8 | done | Unplanned
5 | Controller | Notes | Canvas | Research and Implement Canvas Class | 4 | Chanly | 4 | done
6 | Controller | Notes | Canvas | Save Canvas as Image | 8 | Chanly | 6 | done
7 | Model | General |  | Initial Sync with SegHIS - get all data from SegHIS database based on doctor info and save to localhost(encounters) | 8 | Chanly | 8 | done
8 | Controller | Canvas | Image Templates | Erase Everything in the image template | 2 | Chanly | 1 | done | Unplanned
9 | Controller | User Management | Initialization | Design Schema | 6 | Christian | 6 | done
10 | Controller | User Management | Initialization | Initialize Database V2.0 | 8 | Christian | 8 | done
11 | Controller | User Management | Initialization | Generate clientid | 4 | Christian | 3 | done
12 | Controller | User Management | Registration | Store token to database | 2 | Christian | 2 | done
13 | Controller | Patient | Patient List | Search Patient - add functionality | 10 | Ipong | 12 | done
14 | Controller | Patient | Patient List | Search Patient - create search patient function | 3 | Jake | 3 | done
15 | Technical Investigation | Patient | Patient Encounter | Retrieve and Display Medical History (spike) | 4 | Jake | 4 | done
16 | Controller | Patient | Patient Encounter | Retrieve and Display Medical History - Expandable List Adapter | 8 | Jake | 8 | done
17 | Controller | Patient | Patient Encounter | Retrieve and Display Medical History - Medical History Expandable List | 5 | Jake | 5 | done
18 | Controller | Patient | Patient List | Search Patient - create patient model class | 3 | Jessie | 3 | done
19 | Controller | Patient | Encounter List | Display Encounter List - create encounter model class | 3 | Jessie | 3 | done
20 | Controller | Patient | Encounter List | Retrieve and Display Patient Info | 10 | Jessie | 12 | done
|  | Patient | Encounter List | Retrieve and Display Patient Info - fixed correct display of Age | 2 | Jake | 2
21 | Controller | Notes | Canvas | Modification and Debugging | 4 | Justine | 4 | done
22 | Controller | Notes | Canvas | Retrieve from external memory | 8 | Justine | 6 | done
23 | Model | General |  | Initial Sync with SegHIS - get all data from SegHIS database based on doctor info and save to localhost(departments) | 8 | Justine | 8 | done
24 | Controller | Canvas | Image Templates | Erase Everything in the image template | 2 | Justine | 1 | done | Unplanned
25 | View | User Management | Registration | Login/Registration - four inputs | 3 | Philipp | 3 | done
26 | View | Patient |  | Patient List V2.0 | 4 | Philipp | 2 | done
27 | View | Patient |  | Patient Info V2.0 | 4 | Philipp | 2 | done
28 | View | Patient |  | Patient Encounter V2.0 | 4 | Philipp | 2 | done
29 | View | User Management | Registration | Login/Registration - four inputs (enhancements) | 1 | Philipp | 1 | done | Unplanned
30 | Controller | User Management | Login | Comparison of stored token and received token from API | 8 | Philipp | 6 | done
31 | Controller | Patient | Patient List | Display Patient List | 8 | Ipong | 6 | done
32 | View | Laboratory |  | Set Laboratory Request | 8 | Philipp | 8 | done
33 |  |  |  | Create token JSON Parser | 3 | Alvin | 3 | done | Unplanned
34 | Controller | Canvas | Enhancements | Stretch Image | 3 | Chanly |  | backlogged | Unplanned
35 | Controller | Patient | Patient Encounter | Retrieve and Display Medical History - Prior Requests Expandable List | 5 | Jake |  | backlogged
36 | Controller | Canvas | Enhancements | Stretch Image | 3 | Justine |  | backlogged | Unplanned
37 | Controller | User Management | Login | Login Handling | 3 | Christian |  | backlogged | Unplanned
38 | Model | User Management | Registration | Registration Handling | 3 |  |  | backlogged | Unplanned
39 | Controller | Patient | Patient Encounter | Retrieve and Display Medical History - Referrals Expandable List | 5 |  |  | backlogged
40 | Controller | Patient | Patient Encounter | Retrieve and Display Medical History - Notes Expandable List | 5 |  |  | backlogged
41 | Controller | Patient | Patient Encounter | Retrieve and Display Patient Info | 10 |  |  | backlogged
42 | Technical Investigation | Patient | Patient Encounter | Retrieve and Display Previous Lab Request Info(spike) | 4 | Ipong |  | backlogged
43 | Controller | Patient | Patient Encounter | Retrieve and Display Previous Lab Request Info | 8 |  |  | backlogged
44 | Technical Investigation | Patient | Patient Encounter | Retrieve and Display Referral History(spike) | 4 |  |  | backlogged
45 | Controller | Patient | Patient Encounter | Retrieve and Display Referral History | 6 |  |  | backlogged
46 | Technical Investigation | Patient | Patient Encounter | Retrieve and Display Doctor's Notes (Text) | 4 | Jessie |  | backlogged
47 | Controller | Patient | Patient Encounter | Retrieve and Display Doctor's Notes (Text) | 10 |  |  | backlogged
|  |  |  | TOTAL | 248 |  | 162 | 65.32%
|  |  |  | GOALS | STATUS
|  |  |  | Doctor can now view encounter list for every patient | partial
|  |  |  | Doctor can now register and have a successful login using dummy data(depends on API arrival) | partial
|  |  |  | Doctor can now save a free hand note and view it after saving | done
|  |  | Member Name | Actual Hours Done | Target
|  |  | Chanly Basa | 19 | 22
|  |  | Justine Yu | 19 | 22
|  |  | Philipp Monteverde | 16 | 24
|  |  | Jose Ipong | 18 | 18
|  |  | Jake Muncada | 20 | 20
|  |  | Jessie Adante | 18 | 16
|  |  | Christian Dalisay | 19 | 20
|  |  | Alvin Cosare | 20 | 20
|  |  | TOTAL | 149 | 162

## Sprint 3
# | Type | Module | Section | Description | Target Hrs. | Assignee | Actual Hrs. | Status
1 | Controller | Preferences | Shared | Setup Shared Preferences | 1 | Christian | 1 | dcne
2 | Controller | Preferences | Shared | Setup Shared Preferences | 1 | Alvin | 1 | done
3 | Controller | Preferences | Login | Remember Me | 4 | Christian | 4 | dcne
4 | Controller | Preferences | Registration | Error Trap Network Connectivity Registration | 2 | Alvin | 2 | done
5 | Controller | Preferences | Network | Create Method for checking internet access | 1 | Alvin | 1 | done
6 | Controller | Patient | Patient Encounter | Retrieve and Display Medical History - Prior Requests Expandable List | 5 | Jake | 5 | done
7 | Controller | Canvas | Enhancements | Stretch Image | 3 | Justine | 3 | done
8 | Controller | Canvas | Enhancements | Stretch Image | 3 | Chanly | 3 | done
9 | Controller | User Management | Login | Login Handling | 3 | Christian | 6 | done
10 | Model | User Management | Registration | Registration Handling | 3 | Christian | 3 | done
11 | Controller | Patient | Patient Encounter | Retrieve and Display Medical History - Referrals Expandable List | 5 |  |  | to do
12 | Controller | Patient | Patient Encounter | Retrieve and Display Medical History - Notes Expandable List | 5 |  |  | to do
13 | Controller | Patient | Patient Encounter | Retrieve and Display Patient Info | 10 |  |  | to do
14 | Technical Investigation | Patient | Patient Encounter | Retrieve and Display Previous Lab Request Info(spike) | 4 |  |  | to do
15 | Controller | Patient | Patient Encounter | Retrieve and Display Previous Lab Request Info | 8 | Jake |  | ongoing
16 | Technical Investigation | Patient | Patient Encounter | Retrieve and Display Referral History(spike) | 4 |  |  | to do
17 | Controller | Patient | Patient Encounter | Retrieve and Display Referral History | 6 |  |  | to do
18 | Technical Investigation | Patient | Patient Encounter | Retrieve and Display Doctor's Notes (Text) | 4 | Jessie | 5 | done
19 | Technical Investigation | Patient | Patient Encounter | Retrieve Doctors Notes thru web service (GET) spike | 4 |  |  | to do
20 | API | Patient | Patient Encounter | Retrieve Doctors Notes thru web service (GET) | 8 |  |  | to do
21 | Controller | Patient | Patient Encounter | Retrieve and Display Doctor's Notes (Text) | 10 | Jessie | 10 | done
22 | Controller | Patient | Patient List | Display Patient List (Online) | 5 | Ipong | 5 | done
23 | Controller | Patient | Patient List | Display Patient List (Online) | 5 | Justine | 5 | done
24 | Model | Tagging | Tag as my patient | Create Model Class for TAG | 2 | Alvin | 2 | done
25 | Controller | Tagging | Tag as my patient | Handle click of tag button - call method or start new activity and also button change | 5 | Alvin | 3 | done
26 | API | Tagging | Tag as my patient | Submit Tag thru web service (POST) | 8 | Alvin | 8 | done
27 | API | Tagging | Tag as my patient | Retrieve data for specific encounter thru web service (GET) | 6 | Christian | 4 | done
28 | Model | Tagging | Tag as my patient | Save data into mobile DB | 4 | Christian | 2 | done
29 | Controller | Tagging | Undo Tag | Handle click of undo tag button - call method or start new activity and also button change | 5 | Alvin | 3 | done
30 | API | Tagging | Undo Tag | Update status of tag thru web service (PUT)? | 6 | Alvin | 6 | done
31 | Model | Tagging | Undo Tag | Delete associated data in mobile DB - based on encounter_nr | 4 | Christian | 2 | done
32 | Controller | Laboratory | Patient Search | Integrate search with lab | 2 | Ipong | 2 | done
33 | Model | Laboratory | Classes | Create Lab request model class - Enhancements | 2 | Jessie | 1 | done
34 | Model | Laboratory | Classes | Create Lab service model class - Enhancements | 2 | Jessie |  | to do
35 | Model | Laboratory | Classes | Retrieve lab requests info from mobile DB | 8 |  |  | to do
36 | Controller | Laboratory | Request List | Display Summary Info - patient info | 6 | Ipong |  | ongoing
37 | Controller | Laboratory | Request List | Display Summary Info - request list | 6 |  |  | to do
38 | Controller | Laboratory | Request List | Delete Request from list | 6 |  |  | to do
39 | Controller | Laboratory | Add Request/Service List | Display Specific Request - request info | 6 |  |  | to do
40 | Controller | Laboratory | Add Request/Service List | Display Specific Request - services list | 6 |  |  | to do
41 | Controller | Laboratory | Add Request/Service List | Add service functionality | 5 |  |  | to do
42 | Controller | Laboratory | Add Request/Service List | Empty Services List Functionality | 4 |  |  | to do
43 | Controller | Laboratory | Add Request/Service List | Compute Total charge - based on services included | 8 |  |  | to do
44 | View | Laboratory | Add Service | Create layout for add service | 8 | Philipp | 8 | done
45 | API | Laboratory |  | Post added lab requests info thru web service (POST) | 8 |  |  | to do
46 | View | Referral | Add referral | Create Add referral layout | 8 | Philipp | 8 | done
47 | Controller | Referral | Add referral | Make Referral | 6 | Justine |  | testing
48 | Model | Referral | Display referrals | Retrieve previous referrals | 6 | Christian |  | ongoing
49 | Controller | Referral | Display referrals | Display previous referrals | 6 |  |  | to do
50 | API | Syncing | Manual Syncing | Retrieve new laboratory request | 8 |  |  | to do
51 | API | Syncing | Manual Syncing | Retrieve new text notes | 8 |  |  | to do
52 | API | Syncing | Manual Syncing | Retrieve new encounters | 8 |  |  | to do
53 | API | Syncing | Manual Syncing | Retrieve new referrals | 8 |  |  | to do
54 | View | Doctors Notes | Notes Form | Create layout for adding notes in text form | 6 | Philipp | 8 | done
55 | API | Encounters | Patient - Encounter | Create class Encounter (API) - link patient list to encounter-list | 3 | Ipong | 3 | done
56 | API | Referral | Initial Sync | Retrieve Departments (Initial Sync) | 2 | Justine | 2 | done
57 | Model | Referral | Departments | Store and Retrieve Departments to and from DB | 8 | Christian | 4 | done
58 | Model | Encounters | Tag as my patient | Retrieve tagged encounters | 8 | Alvin |  | testing
59 | Controller | Patients | Online Search | Online search of patients | 8 | Chanly | 10 | done
60 | User Management | Initialization | Database | Internal Schema, Database Initialization, Dummy data - Enhancements | 3 | Christian | 3 | done
|  |  |  | Edit Patient List - Search Patient | 1 | Ipong | 1 | done
|  |  |  | Transfer Expandable List View to Patient Info | 2 | Jake | 1 | done
|  |  |  | Transfer Expandable List View to Patient Info | 2 | Jessie | 1 | done
|  |  |  | Retrieve Latest Encounter (Online) | 4 | Alvin | 4 | done
|  |  |  | TOTAL | 317 |  | 140 | 44.16%
|  |  |  | GOALS | STATUS
|  |  | Member Name | Actual Hours Done | Target
|  |  | Chanly Basa | 13 | 11
|  |  | Justine Yu | 10 | 10
|  |  | Philipp Monteverde | 24 | 22
|  |  | Jose Ipong | 11 | 11
|  |  | Jake Muncada | 6 | 7
|  |  | Jessie Adante | 17 | 18
|  |  | Christian Dalisay | 24 | 31
|  |  | Alvin Cosare | 30 | 34
|  |  | TOTAL | 135 | 144

## Burn Down
Description | Target Hrs. | 2014-05-13 | 2014-05-14 | 2014-05-15 | 2014-05-16
Setup Shared Preferences | 1 | 1 | 0 | 0 | 0
Setup Shared Preferences | 1 | 1 | 0 | 0 | 0
Remember Me | 3 | 3 | 0 | 0 | 0
Error Trap Network Connectivity Registration | 2 | 2 | 0 | 0 | 0
Create Method for checking internet access | 1 | 1 | 0 | 0 | 0
Retrieve and Display Medical History - Prior Requests Expandable List | 5 | 5 | 5 | 0 | 0
Stretch Image | 3 | 0 | 0 | 0 | 0
Stretch Image | 3 | 0 | 0 | 0 | 0
Login Handling | 3 | 0 | 0 | 0 | 0
Registration Handling | 3 | 0 | 0 | 0 | 0
Retrieve and Display Medical History - Referrals Expandable List | 5 | 5 | 5 | 5 | 5
Retrieve and Display Medical History - Notes Expandable List | 5 | 5 | 5 | 5 | 5
Retrieve and Display Patient Info | 10 | 10 | 10 | 10 | 10
Retrieve and Display Previous Lab Request Info(spike) | 4 | 4 | 4 | 4 | 4
Retrieve and Display Previous Lab Request Info | 8 | 8 | 8 | 8 | 8
Retrieve and Display Referral History(spike) | 4 | 4 | 4 | 4 | 4
Retrieve and Display Referral History | 6 | 6 | 6 | 6 | 6
Retrieve and Display Doctor's Notes (Text) | 4 | 4 | 0 | 0 | 0
Retrieve Doctors Notes thru web service (GET) spike | 4 | 4 | 4 | 4 | 4
Retrieve Doctors Notes thru web service (GET) | 8 | 8 | 8 | 8 | 8
Retrieve and Display Doctor's Notes (Text) | 10 | 10 | 10 | 10 | 0
Display Patient List (Online) | 5 | 5 | 0 | 0 | 0
Display Patient List (Online) | 5 | 5 | 0 | 0 | 0
Create Model Class for TAG | 2 | 2 | 0 | 0 | 0
Handle click of tag button - call method or start new activity and also button change | 5 | 5 | 0 | 0 | 0
Submit Tag thru web service (POST) | 8 | 8 | 8 | 0 | 0
Retrieve data for specific encounter thru web service (GET) | 6 | 6 | 6 | 6 | 0
Save data into mobile DB | 4 | 4 | 0 | 0 | 0
Handle click of undo tag button - call method or start new activity and also button change | 5 | 5 | 5 | 0 | 0
Update status of tag thru web service (PUT)? | 6 | 6 | 6 | 0 | 0
Delete associated data in mobile DB - based on encounter_nr | 4 | 4 | 4 | 4 | 0
Integrate search with lab | 2 | 2 | 2 | 2 | 0
Create Lab request model class | 2 | 2 | 2 | 2 | 0
Create Lab service model class | 2 | 2 | 2 | 2 | 2
Retrieve lab requests info from mobile DB | 8 | 8 | 8 | 8 | 8
Display Summary Info - patient info | 6 | 6 | 6 | 6 | 6
Display Summary Info - request list | 6 | 6 | 6 | 6 | 6
Delete Request from list | 6 | 6 | 6 | 6 | 6
Display Specific Request - request info | 6 | 6 | 6 | 6 | 6
Display Specific Request - services list | 6 | 6 | 6 | 6 | 6
Add service functionality | 5 | 5 | 5 | 5 | 5
Empty Services List Functionality | 4 | 4 | 4 | 4 | 4
Compute Total charge - based on services included | 8 | 8 | 8 | 8 | 8
Create layout for add service | 8 | 8 | 0 | 0 | 0
Post added lab requests info thru web service (POST) | 8 | 8 | 8 | 8 | 8
Create Add referral layout | 8 | 8 | 8 | 0 | 0
Make Referral | 6 | 6 | 6 | 6 | 6
Retrieve previous referrals | 6 | 6 | 6 | 6 | 6
Display previous referrals | 6 | 6 | 6 | 6 | 6
Retrieve new laboratory request | 8 | 8 | 8 | 8 | 8
Retrieve new text notes | 8 | 8 | 8 | 8 | 8
Retrieve new encounters | 8 | 8 | 8 | 8 | 8
Retrieve new referrals | 8 | 8 | 8 | 8 | 8
Create layout for adding notes in text form | 6 | 0 | 0 | 0 | 0
Create class Encounter (API) | 3 | 0 | 3 | 0 | 0
Retrieve Departments (Initial Sync) | 2 | 0 | 0 | 0 | 0
Store Departments to DB | 8 | 0 | 2 | 0 | 0
Retrieve tagged encounters | 8 | 0 | 8 | 8 | 8
Online search of patients | 8 | 0 | 8 | 0 | 0
Internal Schema and Dummy data - Enhancements | 3 | 0 | 0 | 0 | 0
Transfer Expandable List View to Patient Info | 2 | 0 | 0 | 0 | 0
Transfer Expandable List View to Patient Info | 2 | 0 | 0 | 0 | 0
Estimated Hours Remaining | 278 | 208.5 | 139 | 69.5 | 0
Actual Hours Remaining | 278 | 266 | 246 | 201 | 0

## Burn Down 3
# | Type | Module | Section | Description | Target Hrs. | Assignee | Hrs. Done | Status
| Model | General |  | Initialize Database - create localhost database (based on Final ERD wiith indexing) | 12 | Christian | 12 | done
| Model | General | Registration | Create API - for retrieving doctor's credentials from SegHIS |  |  |  | pending
| Model | General |  | Populate Database with Dummy Data - populate encounters and patient | 8 | Christian |  | testing
| Model | General | Patient List | Create API - for retrieving doctor's tagged patient from SegHIS |  |  |  | pending
| View | User Management | Registration | Login/Registration - four inputs () | 3 | Philipp | 3 | done
| View | Patient |  | Patient List V2.0 | 2 | Philipp | 2 | done
| View | Patient |  | Patient Info V2.0 | 2 | Philipp | 2 | done
| View | Patient |  | Patient Encounter V2.0 | 2 | Philipp | 2 | done
| Controller | Patient | Patient List | Search Patient - add functionality |  | Ipong |  | to do
| Controller | Patient | Patient List | Search Patient - create patient model class |  | Jessie |  | to do
| Controller | Patient | Encounter List | Display Encounter List - create encounter model class |  | Jake |  | to do
| Controller | Patient | Patient List | Display Patient List |  | Jessie |  | to do
| Controller | Patient | Encounter List | Retrieve and Display Patient Info |  | Jessie |  | to do
| Controller | Patient | Patient Encounter | Retrieve and Display Patient Info |  | Jessie |  | to do
| Controller | Patient | Patient Encounter | Retrieve and Display Medical Info |  | Ipong |  | to do
| Controller | Patient | Patient Encounter | Retrieve and Display Previous Lab Request Info |  | Ipong |  | to do
| Controller | Patient | Patient Encounter | Retrieve and Display Referral History |  | Jake |  | to do
| Controller | Patient | Patient Encounter | Retrieve and Display Doctor's Notes (Text) |  | Jake |  | to do
| Controller | Notes | Canvas | Research and Implement Canvas Class | 2 | Chanly | 2 | done
| Controller | Notes | Canvas | Save Canvas as Image |  | Chanly |  | to do
| Controller | Notes | Canvas | Retrieve from external memory |  | Justine |  | to do
| Controller | Notes | Canvas | Modification and Debugging | 2 | Justine | 2 | done

## Sheet2
| Type | Module | Section | Description | Target Hrs. | Assignee | Hrs. Done | Status
1 | Model | General |  | Initialize Database - create localhost database (based on Final ERD) |  | Christian |  | to do
2 | Model | User Management | Registration | Create API - for retrieving doctor's credentials from SegHIS |  | Jake |  | to do
3 | Model | Patient(Offline) | Patient List | Create API - for retrieving doctor's tagged patient from SegHIS |  | Alvin |  | to do
4 | View | User Management | Registration | Personnel number - doctor can input his personnel_number |  | Louie |  | to do
5 | Model | User Management | Registration | Validate Personnel Number - validate personnel number if it exists in SegHIS |  | Dulce |  | to do
6 | Model | User Management | Registration | Get Username and Password - retrieve username and password from SegHIS based on personnel number |  | Jake |  | to do
7 | View | User Management | Registration | Enter Credentials from SegHIS - doctor can input his username and password from SegHIS |  | Joy |  | to do
8 | Controller | User Management | Registration | Credentials verification - compare doctor SegHIS credentials with inputted credentials |  | Dulce |  | to do
9 | Model | General |  | Initial Sync with SegHIS - get all data from SegHIS database based on doctor info and save to localhost(encounters) |  | Chanly |  | to do
10 | Model | General |  | Initial Sync with SegHIS - get all data from SegHIS database based on doctor info and save to localhost(departments) |  | Justine |  | to do
11 | View | User Management | Registration | Create Account - doctor can fill up sign up form(username, password, confirm) |  | Louie |  | to do
12 | Model | User Management | Registration | Create Account - save successful registration credentials to database |  | Christian |  | to do
13 | View | User Management | Login | Login Page - login page ("invalid login" dialog box included) |  | Ipong |  | to do
14 | Controller | User Management | Login | Validate credentials - from database values |  | Dulce |  | to do
15 | View | General | Navigation Bar | Implement Action Bar - implement navigation drawer | 5 | Ipong | 5 | done
16 | View | General | Navigation Bar | Implement Action Bar - add functionality to navigation items | 5 | Justine | 5 | done
17 | View | General | Navigation Bar | Implement Action Bar -add home button | 5 | Ipong | 5 | done
18 | View | General | Home Page | Icons - make icons for home page | 10 | Philipp | 10 | done
19 | View | General | Home Page | Icons - add functionality to icon buttons | 5 | Justine | 5 | done
20 | View | General | Home Page | Icons - add functionality to icon buttons | 5 | Ipong | 5 | done
21 | Controller | General | Logout | Logout - allow doctor to logout (navigation drawer) |  | Gab |  | to do
22 | View | Patient (Offline/Online) | Patient List | Patient List Layout - make layout for patient module first page |  |  |  | to do
23 | Model | Patient (Offline) | Patient List | Search Patient Name - retrieve all names/pid of patient that match search string from localhost |  |  |  | to do
24 | Model | Patient (Online) | Patient List | Search Patient Name - retrieve all names/pid of patient that match search string from SegHIS (with respect to department) |  |  |  | to do
25 | Controller | Patient(Offline/Online) | Patient List | Handle Select Patient - link the patent list page to encounter list page |  |  |  | to do
26 | View | Patient (Offline/Online) | Encounter List | Encounters List Page Layout - make layout for listing all encounters for active patient |  |  |  | to do
27 | Model | Patient (Offline/Online) | Encounter List | Retrieve Encounters - retrieve all encounters of active patient from localhost |  |  |  | to do
28 | Controller | Patient (Offline/Online) | Encounter List | Handle Select Encounter - link encouter list page to patient info |  |  |  | to do
29 | View | Patient (Offline/Online) | Patient Info | Encounter-Patient Info Layout - make layout for encounter-patient info page (with "Tag as my patient" button)) |  |  |  | to do
30 | Model | Patient (Offline/Online) | Patient List -> Patient Info | Get Patient Info - get necessary patient data in patient info page based on active patient (pid) from localhost |  |  |  | to do
31 | Controller | Patient (Offline/Online) | Patient List -> Patient Info | Integrate Patient Data - display necessary patient data for a specific encounter in encounter-patient info page |  |  |  | to do
32 | Controller | Patient(Online) | Patient Tagging | Handle Tag Patient - handle click of "tag as my patient" button |  |  |  | to do
33 | Model | Patient(Online) | Patient Tagging | Handle Tag Patient - update localhost and SegHIS database (POST method) |  |  |  | to do
34 | View | Patient (Offline/Online) | Referral | Referral History - make layout for referral history |  |  |  | to do
35 | View | Patient(Online) | Referral | Referral Request - make layout for making a referral request |  |  |  | to do
36 | Model | Patient(Offline/Online) | Referral | Retrieve Referrals - retrieve all referrals of active patient from localhost

## Sheet3
43 | View | Laboratory | Request | View Previous Requests - make layout for viewing previously made requests (with "Add new request" button at bottom)
44 | Model | Laboratory | Request | Retrieve Existing Requests - retrieve all existing requests from localhost/SegHIS?
45 | Controller | Laboratory | Request | Select an Existing Request - redirect doctor to a page containing existing info about a request if existing request is clicked
46 | Model | Laboratory | Request | Update Existing Request - handle update of request in SegHIS (PUT)
47 | Model | Laboratory | Request | Update Existing Request - handle update of request in localhost
48 | View | Laboratory | Request | Make New Request - make layout for making a new lab request
49 | Controller | Laboratory | Request | Setup New Request - setup options for making a new request
50 | Controller | Laboratory | Request | Submit New Request - handle submit new lab request to SegHIS (POST)
51 | Controller | Laboratory | Request | Save New Request - save new request in localhost
52 | View | Laboratory | Request | Add New Service - make layout for adding a service to a lab request
53 | Controller | Laboratory | Request | Setup New Service - setup options for choosing a new service
54 | View | Notes | SOAP | SOAP Layout - make layout for doctor's notes
55 | Model | Notes | SOAP | Setup SOAP notes - setup texts in SOAP if it exists
56 | Model | Notes | SOAP | Submit SOAP notes - submit SOAP notes to SegHIS?
57 | Model | Notes | SOAP | Save SOAP notes - save SOAP notes to localhost
58 | View | Notes | Canvas | Canvas options - make layout for canvas options (Add new/View existing)
59 | View | Notes | Canvas | Making Canvas - make layout for canvas making (Save/Discard)
60 | Model | Notes | Canvas | Save Canvas - save canvas in external memory
61 | Model | Notes | Canvas | Save Canvas - save canvas uri in localhost

## Burn Down 2
# | Description | Target Hrs. | 2014-05-07 | 2014-05-08 | 2014-05-09
| Setup Registration Activity | 8
Unplanned | Setup Login Activity | 2
Unplanned | Save Client ID to database | 6
Unplanned | Retrieve Tokens
| Research and Implement Canvas Class | 4
| Save Canvas as Image | 8
| Initial Sync with SegHIS - get all data from SegHIS database based on doctor info and save to localhost(encounters) | 8
Unplanned | Zoom functionality
Unplanned | Erase Everything in the image template | 2
| Design Schema | 6
| Initialize Database V2.0 | 8
| Generate clientid | 4
| Store token to database | 2
| Search Patient - add functionality | 10
| Search Patient - create search patient function | 3
| Retrieve and Display Medical History (spike) | 4
| Retrieve and Display Medical History | 10
| Search Patient - create patient model class | 3
| Display Encounter List - create encounter model class | 3
| Retrieve and Display Patient Info | 10
| Modification and Debugging | 4
| Retrieve from external memory | 8
| Initial Sync with SegHIS - get all data from SegHIS database based on doctor info and save to localhost(departments) | 8
Unplanned | Zoom functionality
Unplanned | Erase Everything in the image template | 2
| Login/Registration - four inputs | 3
| Patient List V2.0 | 4
| Patient Info V2.0 | 4
| Patient Encounter V2.0 | 4
Unplanned | Login/Registration - four inputs (enhancements) | 2
| Comparison of stored token and received token from API | 8
| Display Patient List | 8
| Retrieve and Display Patient Info | 10
| Retrieve and Display Previous Lab Request Info(spike) | 4
| Retrieve and Display Previous Lab Request Info | 8
| Retrieve and Display Referral History(spike) | 4
| Retrieve and Display Referral History | 6
| Retrieve and Display Doctor's Notes (Text) | 4
| Retrieve and Display Doctor's Notes (Text) | 10
| Retrieve token API/Dummy Data (depends) | 8
Patient List V2.0
| Estimated Hours | 89 | 0 | 0 | 0
| Remaining Hours | 89 | 0 | 0 | 0